BOARD EXECUTIVE BRIEFING 5-Year Risk-Based Capital Plan Consolidated Portfolio ¦ Canada & United States ¦ 2026–2030 Prepared by Roth IAMS ¦ March 2026 ¦ Annual Budget: $5,000,000 USD

| Total Portfolio Assets | Combined Replacement Value | 5-Year Budget Envelope | 5-Year Plan Cost |
| --- | --- | --- | --- |
| 21 Buildings | $1.705B USD | $25.0M USD | $21.4M USD |

# 1.  Purpose of This Briefing

This briefing has been prepared in advance of the Board presentation to provide directors with context on the financial condition of the Roth IAMS-managed facility portfolio across Canada and the United States. The document summarizes the current state of the portfolio, the methodology used to prioritize capital investment, and the recommended 5-Year Capital Plan for Board review and endorsement.

All values are expressed in United States Dollars (USD). Canadian portfolio values have been converted at the Bank of Canada mid-market rate of 0.7297 CAD/USD as of March 24, 2026. Future-year costs are escalated at 3% per annum from the 2026 base year to reflect construction cost inflation.

# 2.  Portfolio Overview

Roth IAMS manages a consolidated portfolio of 21 buildings across Canada and the United States, representing a combined gross floor area of approximately 4.27 million square feet and a total replacement value of $1.705 billion USD. Facility Condition Assessments (FCAs) have been completed for all assets using the SLAM platform, providing a defensible, data-driven baseline for capital planning.

| Metric | Canada (USD) | United States (USD) | Combined (USD) |
| --- | --- | --- | --- |
| Buildings | 10 | 11 | 21 |
| Gross Floor Area | 20.3M sqft | 17.1M sqft | 37.4M sqft |
| Replacement Value | $1.004B | $701M | $1.705B |
| 3-Yr Deferred Capital | $436.7M | $80.9M | $517.6M |
| 3-Year FCI | 43.5% | 11.5% | 30.3% |

The Canadian portfolio carries a significantly elevated Facility Condition Index (FCI) of 43.5%, compared to 11.5% for the US portfolio. This disparity reflects the age and deferred maintenance profile of the Canadian assets, several of which were constructed in the late 1920s through 1970s and have accumulated substantial renewal backlogs. The combined portfolio FCI of 30.3% places the portfolio in the “Poor” band under standard industry benchmarking, exceeding the 25% threshold that typically triggers urgent Board-level capital action.

FCI Benchmark Reference: Standard industry interpretation of Facility Condition Index scores:

- Good (< 10%)  Asset is well-maintained; proactive management focus

- Fair (10%–25%)  Moderate deterioration; planned investment required

- Poor (25%–60%)  Significant backlog; risk of accelerated failure; prioritized investment critical

- Critical (> 60%)  Major intervention required; consider disposition or major recapitalization

# 3.  The Capital Challenge

The full scope of renewal needs identified across the consolidated portfolio over the 2026–2030 period totals approximately $452 million USD. Against an annual renewal budget of $5 million, the plan addresses $21.4 million — approximately 4.7% of the total identified need. This underscores a fundamental reality that faces many institutions managing aging facilities: the annual budget is a triage tool, not a solution to the full backlog.

The Board should understand three things clearly:

- The $5M annual budget is sufficient to address the highest-risk life-safety and building envelope items on a risk-prioritized basis.

- The majority of the deferred backlog — approximately $431 million — will continue to accumulate, and costs will escalate at 3% annually if not addressed.

- Without a longer-term capital investment strategy, the portfolio FCI will worsen, operational disruptions will increase, and the eventual cost of intervention will be substantially higher.

⚠ Residual Risk Exposure The Deferred Risk Register (Tab 3 of the attached capital plan workbook) identifies 276 high-risk recommendations — assessed at Poor or Very Poor condition — that cannot be accommodated within the $5M/year budget envelope. Items involving fire alarm, standpipe, and emergency notification systems are of particular concern and may warrant supplemental capital allocation or an accelerated investment scenario. The Board is advised to consider whether a higher annual envelope or a one-time supplemental appropriation is warranted for the Canadian portfolio specifically.

# 4.  Prioritization Methodology

The 5-Year Capital Plan was developed using a risk-based prioritization model applied to the full SLAM recommendation dataset. Each recommendation was scored on four weighted dimensions and ranked in descending order within each annual $5M budget envelope.

| Scoring Dimension | Max Points | Description |
| --- | --- | --- |
| SLAM Priority Rating | 100 | Health & Safety = 100 pts; Imminent Breakdown = 80 pts; Proactive Replacement = 40 pts; Upgrade = 20 pts |
| Element Condition | 50 | Very Poor/Critical = 50 pts; Poor = 35 pts; Fair = 20 pts; Good = 5 pts; Very Good = 2 pts |
| SLAM MVP Score | 20 | Normalized 0–20 from SLAM’s proprietary multi-variable priority algorithm |
| Risk Category Bonus | 30 | Life-safety systems +30; Building envelope +20; Mechanical/electrical systems +15; Security +10 |

Projects were allocated to each year’s budget in descending risk-score order using a greedy allocation algorithm — maximizing life-safety risk reduction per dollar invested, subject to the annual budget constraint. The resulting plan is transparent, auditable, and aligned with recognized asset management standards (ISO 55000).

# 5.  The 5-Year Capital Plan (2026–2030)

The plan encompasses 51 projects across both portfolios, with a total inflation-adjusted cost of $21.4 million against a $25 million total budget envelope. Budget utilization averages 85.6% across the five-year period, with 2029 under-utilized due to the limited number of SLAM-scheduled recommendations in that year.

| Year | # Projects | Budget (USD) | Plan Cost (Infl-Adj) | Remaining | Utilization |
| --- | --- | --- | --- | --- | --- |
| 2026 | 13 | $5,000,000 | $4,998,242 | $1,758 | 100.0% |
| 2027 | 15 | $5,000,000 | $4,986,659 | $13,341 | 99.7% |
| 2028 | 3 | $5,000,000 | $4,920,943 | $79,057 | 98.4% |
| 2029 | 4 | $5,000,000 | $1,541,416 | $3,458,584 | 30.8% |
| 2030 | 16 | $5,000,000 | $4,952,781 | $47,219 | 99.1% |
| TOTAL | 51 | $25,000,000 | $21,400,041 | $3,599,959 | 85.6% |

The 2029 under-utilization ($3.46M remaining) represents a planning opportunity. Management recommends pulling forward high-priority 2030 or 2031 items into 2029, or directing the surplus toward life-safety items currently sitting on the Deferred Risk Register.

## Plan Composition by Risk Category

The plan is weighted heavily toward life-safety and building envelope systems, consistent with the risk-first mandate:

| Category | Projects | Plan Cost (USD) | % of Plan |
| --- | --- | --- | --- |
| Life Safety & Emergency Systems | 16 | $13,430,495 | 62.8% |
| Building Envelope | 4 | $4,918,557 | 23.0% |
| Mechanical Systems | 5 | $141,699 | 0.7% |
| Security Systems | 6 | $854,286 | 4.0% |
| Other Building Systems | 20 | $2,055,005 | 9.6% |

Life Safety and Emergency Systems account for 62.8% of total plan spend, reflecting the volume of fire alarm, standpipe, emergency lighting, public address, and elevator systems across the Canadian portfolio assessed at Poor or Very Poor condition. Building Envelope items — principally the Mustafar Visitor Center exterior window replacement — account for a further 23.0%.

# 6.  Key Highlights by Year

## 2026 — Immediate Life-Safety Response  ($4,998,242)

- Fire alarm activation, notification devices, and wiring at Bespin Auditorium (Poor condition) — required for code compliance and emergency evacuation.

- Public address and PA systems at Bespin Auditorium — dual-system replacement for emergency notification coverage.

- Wet standpipe system (two components) at Bespin Auditorium — fire suppression infrastructure in Poor condition.

- Exit signs at Humanities Fine Arts and emergency battery pack lighting at Kamino Student Centre.

- Emergency eyewash and shower stations at Bespin Auditorium and Mayo Building — OSHA-required lab safety equipment.

- Exterior concrete stairs at Humanities Fine Arts — fall hazard and accessibility compliance.

- Boiler replacement (1982 and 1990 vintage) at Humanities Fine Arts — end-of-life mechanical life-safety support.

## 2027 — Life-Safety Continuation and Critical Mechanical  ($4,986,659)

- Fire alarm activation devices and wiring at Science Building — largest single life-safety expenditure ($2.7M combined), systems in Poor condition.

- Hydraulic passenger elevator at Science Building (two components) — accessibility compliance and egress risk.

- Emergency battery pack lighting at Lando Gym — required egress illumination on failure of primary power.

- Emergency eyewash stations at Mayo Building — laboratory safety compliance.

- Variable frequency drives for air handling units at Lando Gym — HVAC control system supporting ventilation in Poor condition.

- Exterior automatic door operators at Mayo Building — accessibility compliance.

## 2028 — Major Envelope Renewal  ($4,920,943)

- Exterior windows at The Mustafar Visitor Center ($4.82M) — the single largest project in the plan. Full envelope replacement required to arrest moisture intrusion, energy loss, and accelerating interior system deterioration. Asset was assessed Fair condition; without intervention, condition will deteriorate to Poor within the planning horizon.

- Fixed casework and kitchen cabinets at Humanities Fine Arts and carpet tile at Lando Gym — interior finishes at end of useful life.

## 2029 — Security and Partial Budget Year  ($1,541,416)

- Security card access system at Science Building (Canada) — campus-wide upgrade to access control infrastructure in Fair condition.

- Wet standpipe system (third component) at Bespin Auditorium — completing the fire suppression renewal begun in 2026.

- Science stores A/C at Humanities Fine Arts — mechanical support for controlled-environment storage.

- Acoustic tile ceilings at Lando Gym — interior finishes in Fair condition approaching end of life.

Note: $3.46M of the 2029 budget envelope is unallocated. Management recommends pulling forward priority items from 2030 to optimize annual deployment.

## 2030 — Security and Remaining Life-Safety  ($4,952,781)

- Emergency battery pack lighting at Mayo Building (two systems) — egress compliance.

- Security and intrusion detection systems across multiple assets — campus security infrastructure renewal.

- Humidity control and HVAC support equipment across the portfolio — mechanical systems supporting building environmental controls.

- Water heaters, exhaust fans, and remaining mechanical items reaching end of useful life within the planning horizon.

# 7.  Questions for Board Discussion

Management recommends the Board consider the following questions in the context of this briefing and the accompanying capital plan workbook:

- Annual budget adequacy:  Given the combined portfolio FCI of 30.3% and a $452M total 5-year need, does the Board wish to explore an increased annual capital envelope or a one-time supplemental allocation — targeted at the Canadian portfolio in particular?

- Deferred risk tolerance:  The Deferred Risk Register includes life-safety items that cannot be funded within the $5M constraint. Does the Board wish to direct management to identify supplemental funding sources for these specific items?

- 2029 reallocation:  Management proposes to pull forward high-priority 2030 recommendations into the 2029 budget year to fully deploy the $3.46M under-allocation. Does the Board endorse this approach?

- Canadian portfolio trajectory:  With a 43.5% FCI, the Canadian portfolio is in the “Poor” band. Does the Board wish to establish a target FCI and a multi-year investment strategy to achieve it?

- Reporting cadence:  Management proposes quarterly capital plan progress reports to the Board. Is this frequency acceptable, or would an alternative cadence be preferred?

# 8.  Supporting Materials

The following documents accompany this briefing and are available for Board review prior to and during the presentation:

- Roth_IAMS_Board_Consolidated_Portfolio_2026.xlsx  Consolidated portfolio workbook — all assets, all recommendations, and capital expenditure by year across both portfolios (7 tabs).

- Roth_IAMS_5Year_Capital_Plan_2026–2030.xlsx  5-Year Capital Plan workbook — Executive Summary dashboard, detailed project list with individual selection rationale, and Deferred Risk Register (3 tabs).

Prepared by Roth IAMS Management Facility Asset Management ¦ SLAM Platform Analytics ¦ March 2026 Confidential — For Board Use Only. Not for distribution.