## Executive Summary
Roth IAMS — 5-Year Risk-Based Capital Plan (2026–2030)
Annual Budget: $5,000,000 USD ¦ Priority: Life-Safety → Envelope → Mechanical → Electrical ¦ 3% Inflation ¦ March 24, 2026
Total Projects Selected | 5-Year Budget Envelope | Total Plan Cost (Infl-Adj USD) | Budget Utilization | Avg Annual Spend
51 | $25,000,000 | $21,400,041 | 85.6% | $4,280,008
ANNUAL CAPITAL PLAN SUMMARY
Year | # Projects | Budget (USD) | Plan Cost (Infl-Adj USD) | Remaining Budget (USD) | Budget Used
2026 | 13 | 5000000 | 4998242.0385 | 1757.9615 | 99.96%
2027 | 15 | 5000000 | 4986658.9055 | 13341.0945 | 99.73%
2028 | 3 | 5000000 | 4920943.0629 | 79056.9371 | 98.42%
2029 | 4 | 5000000 | 1541415.6876 | 3458584.3124 | 30.83%
2030 | 16 | 5000000 | 4952781.3359 | 47218.6641 | 99.06%
TOTAL | 51 | 25000000 | 21400041.0304 | 3599958.9696 | 85.6%
PLAN COMPOSITION BY RISK CATEGORY
Risk Category | # Projects | Total Cost (Infl-Adj USD) | % of Plan Budget
Life Safety & Emergency Systems | 16 | 13430494.5915 | 62.76%
Building Envelope | 4 | 4918556.664 | 22.98%
Mechanical Systems | 5 | 141698.9871 | 0.6621%
Security Systems | 6 | 854285.8166 | 3.992%
Other Building Systems | 20 | 2055004.9711 | 9.603%
PRIORITIZATION METHODOLOGY
Projects selected using a composite risk score: SLAM Priority [40–100 pts] + Observed Condition [2–50 pts] + SLAM MVP Score [0–20 pts normalized] + Risk Category Bonus [0–30 pts: life-safety, envelope, mechanical, electrical]. Within each $5M annual budget envelope, projects were selected in descending risk score order. Canadian costs converted CAD→USD at 0.7297 (Bank of Canada, March 24, 2026). Future-year costs escalated at 3%/yr from the 2026 base year.

## Prioritized Capital Plan
5-Year Risk-Based Capital Plan — Detailed Project List (2026–2030)
Annual Budget: $5,000,000 USD ¦ All USD ¦ 3% inflation on future years ¦ CAD→USD 0.7297 ¦ March 24, 2026
PROJECT DETAIL — ALL YEARS
Plan Year | Asset Name | Element / Scope of Work | Uniformat / System | Portfolio | Nominal Cost (USD) | Infl-Adj Cost (USD) | Priority | Condition | Risk Score | MVP Score | Selection Rationale
▶ 2026 ¦ 13 Projects ¦ Budget: $5,000,000 ¦ Plan Cost: $4,998,242 ¦ Remaining: $1,758
2026 | Bespin Auditorium | Fire Alarm System - Activation and Notification Devices | Fire Alarm Systems | Canada | 863737.2941 | 863737.2941 | P4–Proactive Replacement | 4 - Poor | 124.3 | 88 | Selected as highest-priority life-safety system at Bespin Auditorium (Canada portfolio). Fire protection and suppression systems in poor condition pose an immediate risk to occupant safety and regulatory compliance. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 88/91, yielding a composite risk score of 124. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2026 | Bespin Auditorium | Fire Alarm System - Wiring | Fire Alarm Systems | Canada | 863737.2941 | 863737.2941 | P4–Proactive Replacement | 4 - Poor | 124.3 | 88 | Selected as highest-priority life-safety system at Bespin Auditorium (Canada portfolio). Fire protection and suppression systems in poor condition pose an immediate risk to occupant safety and regulatory compliance. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 88/91, yielding a composite risk score of 124. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2026 | Bespin Auditorium | PA System | Public Address and Music Systems | Canada | 1041543.4829 | 1041543.4829 | P4–Proactive Replacement | 4 - Poor | 124.3 | 88 | Selected as highest-priority emergency notification/egress system at Bespin Auditorium (Canada portfolio). Emergency notification and egress systems in poor condition are required by code to ensure safe building evacuation. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 88/91, yielding a composite risk score of 124. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2026 | Bespin Auditorium | Public Address System | Public Address and Music Systems | Canada | 1041543.4829 | 1041543.4829 | P4–Proactive Replacement | 4 - Poor | 124.3 | 88 | Selected as highest-priority emergency notification/egress system at Bespin Auditorium (Canada portfolio). Emergency notification and egress systems in poor condition are required by code to ensure safe building evacuation. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 88/91, yielding a composite risk score of 124. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2026 | Bespin Auditorium | Wet Standpipe System | Standpipes | Canada | 732978.7318 | 732978.7318 | P4–Proactive Replacement | 4 - Poor | 122.8 | 81 | Selected as highest-priority life-safety system at Bespin Auditorium (Canada portfolio). Fire protection and suppression systems in poor condition pose an immediate risk to occupant safety and regulatory compliance. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 81/91, yielding a composite risk score of 123. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2026 | Mayo Building | FM200 System - High Density | Other Fire Protection Systems | Canada | 52173.55 | 52173.55 | P4–Proactive Replacement | 4 - Poor | 122.8 | 81 | Selected as highest-priority building system at Mayo Building (Canada portfolio). Component in poor condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 81/91, yielding a composite risk score of 123. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2026 | Humanities Fine Arts | Exit Signs | Interior Lighting Systems (Industrial) | Canada | 143014.8151 | 143014.8151 | P4–Proactive Replacement | 4 - Poor | 121 | 73 | Selected as highest-priority emergency notification/egress system at Humanities Fine Arts (Canada portfolio). Emergency notification and egress systems in poor condition are required by code to ensure safe building evacuation. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 73/91, yielding a composite risk score of 121. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2026 | Kamino Student Ctr | Emergency Battery Pack Lights | Emergency Lighting Systems | Canada | 229257.1095 | 229257.1095 | P4–Proactive Replacement | 4 - Poor | 120.6 | 71 | Selected as highest-priority emergency notification/egress system at Kamino Student Ctr (Canada portfolio). Emergency notification and egress systems in poor condition are required by code to ensure safe building evacuation. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 71/91, yielding a composite risk score of 121. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2026 | Humanities Fine Arts | Exterior Stairs - Concrete | Exterior (Attached) Stair Construction | Canada | 3948.6183 | 3948.6183 | P4–Proactive Replacement | 4 - Poor | 112.8 | 81 | Selected as highest-priority building envelope at Humanities Fine Arts (Canada portfolio). Building envelope components in poor condition expose the structure to moisture intrusion, energy loss, and accelerated deterioration of interior systems if not addressed. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 81/91, yielding a composite risk score of 113. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2026 | Humanities Fine Arts | Boiler HW - 1982 | Hot Water Boilers - Up to 1000 MBH | Canada | 12622.0003 | 12622.0003 | P4–Proactive Replacement | 4 - Poor | 109.3 | 88 | Selected as highest-priority critical mechanical system at Humanities Fine Arts (Canada portfolio). Core mechanical infrastructure in poor condition risks service disruption to occupants and potential cascading failure of connected systems. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 88/91, yielding a composite risk score of 109. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2026 | Humanities Fine Arts | Boiler HW - 1990 | Hot Water Boilers - Up to 1000 MBH | Canada | 6311.0002 | 6311.0002 | P4–Proactive Replacement | 4 - Poor | 109.3 | 88 | Selected as highest-priority critical mechanical system at Humanities Fine Arts (Canada portfolio). Core mechanical infrastructure in poor condition risks service disruption to occupants and potential cascading failure of connected systems. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 88/91, yielding a composite risk score of 109. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2026 | Humanities Fine Arts | Unit Heaters - Electric | Unit Heaters (Hydronic) | Canada | 6374.6592 | 6374.6592 | P4–Proactive Replacement | 4 - Poor | 88.8 | 63 | Selected as highest-priority building system at Humanities Fine Arts (Canada portfolio). Component in poor condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 63/91, yielding a composite risk score of 89. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2026 | Lysaker Gym | Small Lower Roofs | Conventional - Single Ply Membrane | United States | 1000 | 1000 | P4–Proactive Replacement | 1 - Excellent | 73.2 | 48 | Selected as highest-priority building envelope at Lysaker Gym (United States portfolio). Building envelope components in excellent condition expose the structure to moisture intrusion, energy loss, and accelerated deterioration of interior systems if not addressed. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 48/86, yielding a composite risk score of 73. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
Year 2026 Subtotal |  |  |  |  | 4998242.0385 | 4998242.0385
▶ 2027 ¦ 15 Projects ¦ Budget: $5,000,000 ¦ Plan Cost: $4,986,659 ¦ Remaining: $13,341
2027 | Science | Fire Alarm System - Activation and Notification Devices | Fire Alarm Systems | Canada | 2665327.3655 | 2745287.1864 | P4–Proactive Replacement | 4 - Poor | 123.7 | 85 | Selected as highest-priority life-safety system at Science (Canada portfolio). Fire protection and suppression systems in poor condition pose an immediate risk to occupant safety and regulatory compliance. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 85/91, yielding a composite risk score of 124. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2027 | Lando Gym | Emergency lighting | Emergency Lighting Systems | Canada | 416607.3729 | 429105.5941 | P4–Proactive Replacement | 4 - Poor | 118.6 | 62 | Selected as highest-priority emergency notification/egress system at Lando Gym (Canada portfolio). Emergency notification and egress systems in poor condition are required by code to ensure safe building evacuation. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 62/91, yielding a composite risk score of 119. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2027 | Science | Hydraulic Passenger Elevator - 3-Story | Freight Elevators - Up to 3 Floors (Hydraulic) | Canada | 291094.6604 | 299827.5002 | P4–Proactive Replacement | 4 - Poor | 118.4 | 61 | Selected as highest-priority vertical transportation at Science (Canada portfolio). Elevator systems in poor condition create accessibility compliance risk and potential service disruption to building users. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 61/91, yielding a composite risk score of 118. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2027 | Mayo Building | Emergency Eyewash and Shower Units | Universal/Gender Neutral Washroom Fixtures | Canada | 52062.8034 | 53624.6875 | P4–Proactive Replacement | 4 - Poor | 117.3 | 56 | Selected as highest-priority emergency safety equipment at Mayo Building (Canada portfolio). Emergency eyewash and shower stations in poor condition are an OSHA/regulatory requirement in laboratory environments. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 56/91, yielding a composite risk score of 117. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2027 | Mayo Building | Exterior Doors - Automatic Door Operators | Exterior - Automatic Door Openers | Canada | 92277.0374 | 95045.3486 | P4–Proactive Replacement | 4 - Poor | 108.2 | 60 | Selected as highest-priority building envelope at Mayo Building (Canada portfolio). Building envelope components in poor condition expose the structure to moisture intrusion, energy loss, and accelerated deterioration of interior systems if not addressed. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 60/91, yielding a composite risk score of 108. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2027 | Lando Gym | Variable Frequency Drives - Air Handling Units | Main Service Disconnects | Canada | 37417.0458 | 38539.5572 | P4–Proactive Replacement | 4 - Poor | 101.4 | 52 | Selected as highest-priority critical mechanical system at Lando Gym (Canada portfolio). Core mechanical infrastructure in poor condition risks service disruption to occupants and potential cascading failure of connected systems. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 52/91, yielding a composite risk score of 101. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2027 | Kamino Student Ctr | Lighting Fixtures - Exterior | Interior Lighting Systems (Residential) | Canada | 152213.6614 | 156780.0713 | P4–Proactive Replacement | 4 - Poor | 91.3 | 74 | Selected as highest-priority building system at Kamino Student Ctr (Canada portfolio). Component in poor condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 74/91, yielding a composite risk score of 91. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2027 | Mayo Building | Split System A/C Unit | Refrigerant DX Condensing Units - Under 5 Tons | Canada | 52062.7524 | 53624.6349 | P4–Proactive Replacement | 4 - Poor | 88.8 | 63 | Selected as highest-priority building system at Mayo Building (Canada portfolio). Component in poor condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 63/91, yielding a composite risk score of 89. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2027 | Mayo Building | Unit Heaters - Hot Water | Unit Heaters (Hydronic) | Canada | 45897.5462 | 47274.4726 | P4–Proactive Replacement | 4 - Poor | 88.8 | 63 | Selected as highest-priority building system at Mayo Building (Canada portfolio). Component in poor condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 63/91, yielding a composite risk score of 89. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2027 | University Teaching and Outreach Ctr | Gas-Fired Water Heater | Domestic Water Heat Exchangers | Canada | 748402.7437 | 770854.826 | P4–Proactive Replacement | 4 - Poor | 88.2 | 60 | Selected as highest-priority mechanical support system at University Teaching and Outreach Ctr (Canada portfolio). HVAC support equipment in poor condition risks failure of connected heating and ventilation systems. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 60/91, yielding a composite risk score of 88. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2027 | Sports and Health Ctr | Evaporative Coolers | Refrigerant DX Condensing Units - Under 5 Tons | Canada | 239163.2686 | 246338.1667 | P4–Proactive Replacement | 4 - Poor | 87.1 | 55 | Selected as highest-priority building system at Sports and Health Ctr (Canada portfolio). Component in poor condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 55/91, yielding a composite risk score of 87. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2027 | Kamino Student Ctr | Walk-in Coolers and Freezers | Basketball Backboards - Fixed | Canada | 20238.3244 | 20845.4741 | P4–Proactive Replacement | 4 - Poor | 86.9 | 54 | Selected as highest-priority building system at Kamino Student Ctr (Canada portfolio). Component in poor condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 54/91, yielding a composite risk score of 87. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2027 | Humanities Fine Arts | Polished concrete | Other Floor Finishes | Canada | 8152.1208 | 8396.6845 | P4–Proactive Replacement | 4 - Poor | 86.6 | 53 | Selected as highest-priority building system at Humanities Fine Arts (Canada portfolio). Component in poor condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 53/91, yielding a composite risk score of 87. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2027 | Sports and Health Ctr | Water Heater - 2015 - 105 L | Domestic Water Conditioners - Water Softener Systems | Canada | 10249.8551 | 10557.3508 | P4–Proactive Replacement | 4 - Poor | 85.5 | 48 | Selected as highest-priority building system at Sports and Health Ctr (Canada portfolio). Component in poor condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 48/91, yielding a composite risk score of 86. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2027 | Sports and Health Ctr | Water Heater - Elec- 105 Litres | Domestic Water Conditioners - Water Softener Systems | Canada | 10249.8551 | 10557.3508 | P4–Proactive Replacement | 4 - Poor | 85.5 | 48 | Selected as highest-priority building system at Sports and Health Ctr (Canada portfolio). Component in poor condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 48/91, yielding a composite risk score of 86. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
Year 2027 Subtotal |  |  |  |  | 4841416.4131 | 4986658.9055
▶ 2028 ¦ 3 Projects ¦ Budget: $5,000,000 ¦ Plan Cost: $4,920,943 ¦ Remaining: $79,057
2028 | The Mustafar Visitor Center | Exterior windows | Windows | Canada | 4541957.4862 | 4818562.6971 | P4–Proactive Replacement | 3 - Fair | 86.8 | 31 | Selected as highest-priority building envelope at The Mustafar Visitor Center (Canada portfolio). Building envelope components in fair condition expose the structure to moisture intrusion, energy loss, and accelerated deterioration of interior systems if not addressed. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 31/91, yielding a composite risk score of 87. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2028 | Mayo Building | Handicap Lift - 3-Storey | Wheelchair Lifts | Canada | 50994.6394 | 54100.2129 | P4–Proactive Replacement | 3 - Fair | 71.6 | 53 | Selected as highest-priority building system at Mayo Building (Canada portfolio). Component in fair condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 53/91, yielding a composite risk score of 72. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2028 | Humanities Fine Arts | Fixed Casework - Kitchen Cabinets | Vanities | Canada | 45508.6745 | 48280.1528 | P4–Proactive Replacement | 3 - Fair | 70.1 | 46 | Selected as highest-priority building system at Humanities Fine Arts (Canada portfolio). Component in fair condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 46/91, yielding a composite risk score of 70. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
Year 2028 Subtotal |  |  |  |  | 4638460.8001 | 4920943.0629
▶ 2029 ¦ 4 Projects ¦ Budget: $5,000,000 ¦ Plan Cost: $1,541,416 ¦ Remaining: $3,458,584
2029 | Bespin Auditorium | Wet Standpipe System | Standpipes | Canada | 917736.4222 | 1002835.3674 | P4–Proactive Replacement | 3 - Fair | 105.4 | 70 | Selected as highest-priority life-safety system at Bespin Auditorium (Canada portfolio). Fire protection and suppression systems in fair condition pose an immediate risk to occupant safety and regulatory compliance. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 70/91, yielding a composite risk score of 105. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2029 | Bespin Auditorium | Security System - Card Access | Audio Visual Systems Theater | Canada | 122012.1008 | 133325.9169 | P4–Proactive Replacement | 3 - Fair | 86.9 | 77 | Selected as highest-priority security system at Bespin Auditorium (Canada portfolio). Access control and intrusion detection systems in fair condition compromise building security and occupant protection. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 77/91, yielding a composite risk score of 87. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2029 | Humanities Fine Arts | Science stores A/C | Heat Pumps | Canada | 11686.8898 | 12770.58 | P4–Proactive Replacement | 3 - Fair | 71.4 | 52 | Selected as highest-priority building system at Humanities Fine Arts (Canada portfolio). Component in fair condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 52/91, yielding a composite risk score of 71. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2029 | Lando Gym | Acoustic Tile Ceiling - Exposed T-bar - 2009 | Suspended Acoustic Panel Ceiling | Canada | 359178.2973 | 392483.8233 | P4–Proactive Replacement | 3 - Fair | 67.5 | 34 | Selected as highest-priority building system at Lando Gym (Canada portfolio). Component in fair condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 34/91, yielding a composite risk score of 68. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
Year 2029 Subtotal |  |  |  |  | 1410613.7101 | 1541415.6876
▶ 2030 ¦ 16 Projects ¦ Budget: $5,000,000 ¦ Plan Cost: $4,952,781 ¦ Remaining: $47,219
2030 | Science | Security System - Card Access | Fire Alarm Systems | Canada | 2159253.6793 | 2430259.039 | P4–Proactive Replacement | 3 - Fair | 106.3 | 74 | Selected as highest-priority life-safety system at Science (Canada portfolio). Fire protection and suppression systems in fair condition pose an immediate risk to occupant safety and regulatory compliance. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 74/91, yielding a composite risk score of 106. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2030 | Mayo Building | Emergency Battery Pack Lights | Emergency Lighting Systems | Canada | 499281.4416 | 561945.6612 | P4–Proactive Replacement | 3 - Fair | 103 | 59 | Selected as highest-priority emergency notification/egress system at Mayo Building (Canada portfolio). Emergency notification and egress systems in fair condition are required by code to ensure safe building evacuation. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 59/91, yielding a composite risk score of 103. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2030 | Mayo Building | Emergency Battery Pack Lights | Emergency Lighting Systems | Canada | 539097.9234 | 606759.4623 | P4–Proactive Replacement | 3 - Fair | 103 | 59 | Selected as highest-priority emergency notification/egress system at Mayo Building (Canada portfolio). Emergency notification and egress systems in fair condition are required by code to ensure safe building evacuation. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 59/91, yielding a composite risk score of 103. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2030 | Lando Gym | Emergency Battery Pack Lights | Emergency Lighting Systems | Canada | 342101.172 | 385037.883 | P4–Proactive Replacement | 3 - Fair | 101.2 | 51 | Selected as highest-priority emergency notification/egress system at Lando Gym (Canada portfolio). Emergency notification and egress systems in fair condition are required by code to ensure safe building evacuation. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 51/91, yielding a composite risk score of 101. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2030 | Bespin Auditorium | Security System - Card Access | Audio Visual Systems Theater | Canada | 122012.1008 | 137325.6944 | P4–Proactive Replacement | 3 - Fair | 86.9 | 77 | Selected as highest-priority security system at Bespin Auditorium (Canada portfolio). Access control and intrusion detection systems in fair condition compromise building security and occupant protection. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 77/91, yielding a composite risk score of 87. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2030 | Bespin Auditorium | Security System - Card Access | Audio Visual Systems Theater | Canada | 122012.1008 | 137325.6944 | P4–Proactive Replacement | 3 - Fair | 86.9 | 77 | Selected as highest-priority security system at Bespin Auditorium (Canada portfolio). Access control and intrusion detection systems in fair condition compromise building security and occupant protection. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 77/91, yielding a composite risk score of 87. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2030 | Bespin Auditorium | Security System - Card Access | Audio Visual Systems Theater | Canada | 122012.1008 | 137325.6944 | P4–Proactive Replacement | 3 - Fair | 86.9 | 77 | Selected as highest-priority security system at Bespin Auditorium (Canada portfolio). Access control and intrusion detection systems in fair condition compromise building security and occupant protection. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 77/91, yielding a composite risk score of 87. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2030 | Bespin Auditorium | Security System - Card Access | Audio Visual Systems Theater | Canada | 122012.1008 | 137325.6944 | P4–Proactive Replacement | 3 - Fair | 86.9 | 77 | Selected as highest-priority security system at Bespin Auditorium (Canada portfolio). Access control and intrusion detection systems in fair condition compromise building security and occupant protection. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 77/91, yielding a composite risk score of 87. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2030 | Science | Security System - Card Access | Audio Visual Systems Theater | Canada | 152515.1297 | 171657.1221 | P4–Proactive Replacement | 3 - Fair | 86.3 | 74 | Selected as highest-priority security system at Science (Canada portfolio). Access control and intrusion detection systems in fair condition compromise building security and occupant protection. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 74/91, yielding a composite risk score of 86. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2030 | Lando Gym | Variable Frequency Drives - Air Handling Units | Main Service Disconnects | Canada | 37417.0458 | 42113.2147 | P4–Proactive Replacement | 3 - Fair | 84 | 41 | Selected as highest-priority critical mechanical system at Lando Gym (Canada portfolio). Core mechanical infrastructure in fair condition risks service disruption to occupants and potential cascading failure of connected systems. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 41/91, yielding a composite risk score of 84. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2030 | Lando Gym | Variable Frequency Drives - Air Handling Units | Main Service Disconnects | Canada | 37417.0458 | 42113.2147 | P4–Proactive Replacement | 3 - Fair | 84 | 41 | Selected as highest-priority critical mechanical system at Lando Gym (Canada portfolio). Core mechanical infrastructure in fair condition risks service disruption to occupants and potential cascading failure of connected systems. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 41/91, yielding a composite risk score of 84. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2030 | Mayo Building | Railings | Exterior Guards and Railings | Canada | 68920.3474 | 77570.4582 | P4–Proactive Replacement | 3 - Fair | 70.8 | 49 | Selected as highest-priority building system at Mayo Building (Canada portfolio). Component in fair condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 49/91, yielding a composite risk score of 71. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2030 | Humanities Fine Arts | Fixed Casework - Kitchen Cabinets | Vanities | Canada | 36221.1916 | 40767.2702 | P4–Proactive Replacement | 3 - Fair | 70.1 | 46 | Selected as highest-priority building system at Humanities Fine Arts (Canada portfolio). Component in fair condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 46/91, yielding a composite risk score of 70. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2030 | Humanities Fine Arts | Fixed Casework - Kitchen Cabinets | Vanities | Canada | 18574.9732 | 20906.296 | P4–Proactive Replacement | 3 - Fair | 70.1 | 46 | Selected as highest-priority building system at Humanities Fine Arts (Canada portfolio). Component in fair condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 46/91, yielding a composite risk score of 70. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2030 | Humanities Fine Arts | Kitchenette Sinks | Sinks | Canada | 6374.6592 | 7174.7351 | P4–Proactive Replacement | 3 - Fair | 69.9 | 45 | Selected as highest-priority building system at Humanities Fine Arts (Canada portfolio). Component in fair condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 45/91, yielding a composite risk score of 70. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
2030 | Humanities Fine Arts | Water Coolers | Bidets | Canada | 15259.0559 | 17174.2018 | P4–Proactive Replacement | 3 - Fair | 69.9 | 45 | Selected as highest-priority building system at Humanities Fine Arts (Canada portfolio). Component in fair condition has been scheduled based on its risk score, MVP score, and proximity to end of useful life. Assigned SLAM Priority 4 — Proactive Replacement with MVP Score 45/91, yielding a composite risk score of 70. Deferred renewal would escalate remediation costs at 3% annually and increase operational liability exposure.
Year 2030 Subtotal |  |  |  |  | 4400482.0681 | 4952781.3359
5-YEAR TOTAL |  |  |  |  | 20289215.03 | 21400041.0304

## Deferred Risk Register
Deferred Risk Register — High-Risk Items Excluded Due to $5M/Year Budget Constraint
These items exceed the annual budget. Costs are inflation-adjusted USD. Life-safety items flagged ⚠ should be prioritized for supplemental funding consideration.
Plan Year | Asset Name | Element / Scope of Work | Uniformat / System | Portfolio | Cost (Infl-Adj USD) | Priority | Condition | Risk Notes
2026 | University Teaching and Outreach Ctr | Interior Windows - Metal | Interior Windows | Canada | 10825057.1774 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | University Teaching and Outreach Ctr | Acoustic Tile Ceiling - Exposed T-bar - 1997 | Adhered Acoustic Tile Ceiling | Canada | 9741856.1723 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | University Teaching and Outreach Ctr | HHW Piping | Heating Water Distribution Systems | Canada | 9430867.4236 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | University Teaching and Outreach Ctr | Ductwork Distribution System - 1972 | Air Distribution Systems | Canada | 8042132.1334 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | University Teaching and Outreach Ctr | Ductwork Distribution System | Air Distribution Systems | Canada | 7476023.3867 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | University Teaching and Outreach Ctr | Branch Wiring - Equipment & Devices | Branch Wiring Systems | Canada | 7200185.5347 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | University Teaching and Outreach Ctr | Ductwork Distribution System | Air Distribution Systems | Canada | 7047600.799 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | University Teaching and Outreach Ctr | Lab Acid Waste System - Glass Pipe | Acid Waste Systems | Canada | 6667371.6491 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | University Teaching and Outreach Ctr | Branch Wiring - Equipment & Devices - Average Density - 1972 | Branch Wiring Systems | Canada | 6360215.8174 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | University Teaching and Outreach Ctr | Branch Wiring - Equipment & Devices | Branch Wiring Systems | Canada | 5912501.9829 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Eggcrate Ceiling - Exposed T-bar | Suspended Acoustic Panel Ceiling | Canada | 5718581.9312 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Heating Hot Water Piping | Heating Water Distribution Systems | Canada | 5619050.6031 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Branch Wiring - Equipment & Devices | Branch Wiring Systems | Canada | 5573678.886 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | University Teaching and Outreach Ctr | Ductwork Distribution System | Air Distribution Systems | Canada | 5487157.7076 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Interior Windows - Metal | Interior Windows | Canada | 4923724.8073 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Lighting Fixtures - Interior | Interior Lighting Systems | Canada | 4786710.6217 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Branch Wiring - Equipment & Devices | Branch Wiring Systems | Canada | 4339583.9112 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Domestic Water Distribution | Domestic Water Piping and Fittings | Canada | 4064466.419 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Painted Wall Finish | Painted Wall Covering | Canada | 3968720.9351 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Ductwork Distribution System | Air Distribution Systems | Canada | 3793164.9441 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Chilled Water Piping | Chilled Water Distribution Systems | Canada | 3435413.1592 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | DDC/Pneumatic System - Hybrid | Direct Digital Control Systems | Canada | 3153111.1504 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Distribution Switchgears - 15kV, 600A | Low Voltage Electrical Service | Canada | 3153111.1504 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Sanitary Waste - Gravity Discharge | Sanitary Waste and Vent Piping and Fittings | Canada | 3151232.0999 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Single-Ply Membrane Roof Cover - Ballasted | Conventional - Single Ply Membrane | Canada | 2995375.7104 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Exterior Windows | Windows | Canada | 2975475.8428 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Painted Wall Finish | Painted Wall Covering | Canada | 2879613.8476 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Lab Acid Waste System - Glass Pipe | Acid Waste Systems | Canada | 2839313.4214 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Painted Wall Finish | Painted Wall Covering | Canada | 2815768.7899 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Sanitary Waste - Gravity Discharge - 1972 | Sanitary Waste and Vent Piping and Fittings | Canada | 2783611.0787 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Vinyl Tile Flooring - 1972 | Vinyl Tile / Sheet Floor | Canada | 2751150.7683 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Wet Standpipe System | Standpipes | Canada | 2748910.0493 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. ⚠ Life-safety system — recommend supplemental funding.
2026 | Science | Painted Wall Finish | Painted Wall Covering | Canada | 2745530.3197 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Branch Wiring - Equipment & Devices | Branch Wiring Systems | Canada | 2739011.3696 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Sanitary Waste - Gravity Discharge | Sanitary Waste and Vent Piping and Fittings | Canada | 2563120.2785 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Wet Standpipe System | Standpipes | Canada | 2545882.1303 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. ⚠ Life-safety system — recommend supplemental funding.
2026 | Science | DDC/Pneumatic System - Hybrid | Direct Digital Control Systems | Canada | 2522443.5169 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Public Address System | Public Address and Music Systems | Canada | 2502808.9901 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. ⚠ Life-safety system — recommend supplemental funding.
2026 | Science | Carpet Tile Flooring | Carpet Floor | Canada | 2485302.0277 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Sanitary Waste - Gravity Discharge | Sanitary Waste and Vent Piping and Fittings | Canada | 2439375.4467 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Roof Drainage - Gravity | Rain Water Drainage Piping and Fittings | Canada | 2392964.4762 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Single-Ply Membrane Roof Cover - Ballasted | Conventional - Single Ply Membrane | Canada | 2335414.5623 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Sanitary Waste - Gravity Discharge | Sanitary Waste and Vent Piping and Fittings | Canada | 2261025.7482 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Wet Standpipe System | Standpipes | Canada | 2199088.4547 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. ⚠ Life-safety system — recommend supplemental funding.
2026 | Sports and Health Ctr | Metal Wall Louvers | Exterior Louvers and Screens | Canada | 2151149.8792 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Domestic Water Distribution | Domestic Water Piping and Fittings | Canada | 2144921.9845 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Interior Windows - Metal | Interior Windows | Canada | 2090553.0226 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | DDC/Pneumatic System - Hybrid | Direct Digital Control Systems | Canada | 2071328.8864 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | DDC/Pneumatic System | Direct Digital Control Systems | Canada | 1952628.872 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Painted Wall Finish | Painted Wall Covering | Canada | 1950434.4743 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Roof Drainage - Gravity | Rain Water Drainage Piping and Fittings | Canada | 1946367.5133 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Eggcrate Ceiling - Exposed T-bar | Suspended Acoustic Panel Ceiling | Canada | 1876821.6232 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Roof Drainage - Gravity | Rain Water Drainage Piping and Fittings | Canada | 1852398.8707 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Eggcrate Ceiling - Exposed T-bar | Suspended Acoustic Panel Ceiling | Canada | 1810403.6944 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Painted Wall Finish | Painted Wall Covering | Canada | 1810262.5266 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Acoustic Tile Ceiling - Exposed T-bar | Adhered Acoustic Tile Ceiling | Canada | 1756040.7014 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Eggcrate Ceiling - Exposed T-bar | Suspended Acoustic Panel Ceiling | Canada | 1750643.4097 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Gypsum Board Ceiling - Fire Resistant | Painted Ceiling Structures | Canada | 1736419.9295 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Domestic Water Distribution - 1972 | Domestic Water Piping and Fittings | Canada | 1731716.2103 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Wet Standpipe System | Standpipes | Canada | 1704677.7971 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. ⚠ Life-safety system — recommend supplemental funding.
2026 | Skytop Detector Building | Epoxy Flooring | Painted / Sealed Floor | Canada | 1650746.7062 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | DDC/Pneumatic System - Hybrid | Direct Digital Control Systems | Canada | 1640865.335 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Gypsum Board Ceiling - Fire Resistant | Painted Ceiling Structures | Canada | 1613906.5612 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Wet Standpipe System | Standpipes | Canada | 1606989.1658 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. ⚠ Life-safety system — recommend supplemental funding.
2026 | Skytop Detector Building | Public Address System | Public Address and Music Systems | Canada | 1587673.3573 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. ⚠ Life-safety system — recommend supplemental funding.
2026 | Skytop Detector Building | Sanitary Waste - Gravity Discharge | Sanitary Waste and Vent Piping and Fittings | Canada | 1475474.7729 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | DDC/Pneumatic System - Hybrid - Average | Direct Digital Control Systems | Canada | 1435151.8209 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Soffit - Plaster on Metal Lath | Exterior Soffits | Canada | 1366428.996 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Roof Drainage - Gravity | Rain Water Drainage Piping and Fittings | Canada | 1361484.3372 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Air Handling Unit - Wine Cellar | Refrigerant Distribution Systems | Canada | 1237721.1315 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Metal Panels | Insulated Metal Sandwich Panels | Canada | 1229187.2608 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Vinyl sheet | Masonry and Stone Floor | Canada | 1225157.135 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Carpet Tile Flooring | Carpet Floor | Canada | 1198289.311 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Painted Wall Finish | Painted Wall Covering | Canada | 1143218.1515 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Insulated Metal Panel Roof Cover | Metal Roofing | Canada | 1091587.0604 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | DDC/Pneumatic System | Direct Digital Control Systems | Canada | 1052680.8429 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Carpet Tile Flooring | Carpet Floor | Canada | 1033895.4972 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Curtain Wall | Curtain Walls / Window Walls | Canada | 1021864.51 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Curtain Walls | Curtain Walls / Window Walls | Canada | 883182.9016 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Terrazzo Flooring - Cast In Place | Terrazzo Floor | Canada | 861557.5781 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | DDC/Pneumatic System - Hybrid - Average | Direct Digital Control Systems | Canada | 840756.2902 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Foundation Wall and Footings - 12-ft. - Full Basement | Basement Walls | Canada | 798134.7248 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Roof Drainage - Gravity | Rain Water Drainage Piping and Fittings | Canada | 797599.5993 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Domestic Water Distribution - 1972 | Domestic Water Piping and Fittings | Canada | 792185.6923 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Insulated Metal Panel Roof Cover | Metal Roofing | Canada | 732545.954 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Insulated Metal Panel Roof Cover | Metal Roofing | Canada | 728291.9125 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Exhaust System - Fume Hoods | Exhaust Fans | Canada | 673655.1288 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | University Teaching and Outreach Ctr | Main Electrical System Transformer | Grounding Methods | Canada | 654798.3528 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Carpet Tile Flooring | Carpet Floor | Canada | 645507.4037 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Interior Windows - Metal | Interior Windows | Canada | 607478.3439 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Server room A/C | Refrigerant DX Condensing Units - Over 20 Tons | Canada | 598672.6673 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Perimeter Heat - Electric Baseboard | Electric Baseboard Heaters | Canada | 586468.6464 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Epoxy Flooring | Painted / Sealed Floor | Canada | 585641.2688 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | University Teaching and Outreach Ctr | Single door | Interior Doors - Hollow Metal or Wood | Canada | 494996.5556 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Central AHU | Air Handling Units - Built- Up - Over 20,000 CFM | Canada | 488699.7189 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Central AHU - Air Handler - 30000 CFM - HC-1 | Air Handling Units - Built- Up - Over 20,000 CFM | Canada | 488699.7189 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Central AHU - Air Handler - Electric Heat - Serves Both B and E Blocks | Air Handling Units - Built- Up - Over 20,000 CFM | Canada | 488699.7189 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Central AHU - D and G Blocks | Air Handling Units - Built- Up - Over 20,000 CFM | Canada | 488699.7189 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Gypsum Board Ceiling - Fire Resistant | Painted Ceiling Structures | Canada | 449033.4167 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Mechanical equipment screens | Exterior Louvers and Screens | Canada | 440573.4573 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Carpet tiles | Carpet Floor | Canada | 438752.936 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Carpet tiles | Carpet Floor | Canada | 437398.3793 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Fixed Casework - Lab Benches | Millwork General | Canada | 422261.4606 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Gypsum Board Ceiling - Fire Resistant | Painted Ceiling Structures | Canada | 421580.7819 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Lighting Fixtures - Exterior | Interior Lighting Systems (Residential) | Canada | 414186.8412 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | University Teaching and Outreach Ctr | Interior Hollow Metal Swing Doors - Single Leaf - Nonrated | Interior Doors - Hollow Metal or Wood | Canada | 404997.1819 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Gypsum Board Ceiling | Painted Ceiling Structures | Canada | 384200.1262 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Interior Hollow Metal Swing Doors - Single Leaf - Non rated | Interior Doors - Hollow Metal or Wood | Canada | 359997.495 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Vinyl Tiles | Vinyl Tile / Sheet Floor | Canada | 358145.1443 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Carpet | Carpet Floor | Canada | 342985.8384 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Vinyl Tile Flooring | Vinyl Tile / Sheet Floor | Canada | 342243.894 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Lighting Fixtures - Exterior | Interior Lighting Systems (Residential) | Canada | 333420.4054 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Painted Concrete | Painted / Sealed Floor | Canada | 332989.7729 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Laboratory Sinks | Sinks | Canada | 318732.96 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Lighting Fixtures - Exterior | Interior Lighting Systems (Residential) | Canada | 309604.6611 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Exit Signs | Interior Lighting Systems (Industrial) | Canada | 300739.7255 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. ⚠ Life-safety system — recommend supplemental funding.
2026 | Science | Hydraulic Passenger Elevator - 2-Storey | Freight Elevators - Up to 3 Floors (Hydraulic) | Canada | 291094.6604 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Transformers - 300 KVA & 225 KVA | Grounding Methods | Canada | 284694.936 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Eggcrate Ceiling - Exposed T-bar | Suspended Acoustic Panel Ceiling | Canada | 280834.1079 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Central AHU - 10000 CFM | Air Handling Units - Modular - Up to 20,000 CFM | Canada | 276222.112 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Central AHU - 2000 CFM | Air Handling Units - Modular - Up to 20,000 CFM | Canada | 276222.112 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Soffit - Plaster on Metal Lath | Exterior Soffits | Canada | 273366.4019 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Perimeter Heat - Electric Baseboard | Electric Baseboard Heaters | Canada | 267735.6864 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Interior Windows | Interior Windows | Canada | 265607.2099 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Perimeter Heat - Electric Baseboard | Electric Baseboard Heaters | Canada | 254986.368 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Perimeter Heat - Electric Baseboard | Electric Baseboard Heaters | Canada | 254986.368 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Perimeter Heat - Electric Baseboard | Finned Tube Radiation Units | Canada | 249380.0829 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Emergency Eyewash and Shower Units | Universal/Gender Neutral Washroom Fixtures | Canada | 244044.3706 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. ⚠ Life-safety system — recommend supplemental funding.
2026 | Kamino Student Ctr | Vinyl Tile Flooring - 2009 | Vinyl Tile / Sheet Floor | Canada | 240486.5066 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Carpet Tile Flooring | Carpet Floor | Canada | 236616.2654 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Vinyl Tile Flooring - 2005 | Vinyl Tile / Sheet Floor | Canada | 218001.3922 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Lighting Fixtures - Exterior | Interior Lighting Systems (Residential) | Canada | 217448.0898 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Distribution Equipment - Motor Control Centres | Main Service Switchboards - 800A to 1600A | Canada | 211488.3162 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Distribution Switchboards, Panelboards and Feeders | Main Service Switchboards - 800A to 1600A | Canada | 211488.3162 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Interior Hollow Metal Swing Doors - Single Leaf - Rated | Interior Doors - Hollow Metal or Wood | Canada | 205433.3531 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Distribution Switchboards | Main Service Switchboards - 800A to 1600A | Canada | 199644.9714 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Distribution Switchboards, Panelboards and Feeders | Main Service Switchboards - 800A to 1600A | Canada | 199644.9714 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Distribution Switchboards, Panelboards and Feeders - 1972 | Main Service Switchboards - 800A to 1600A | Canada | 199644.9714 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Main Distribution Switchboard | Main Service Switchboards - 800A to 1600A | Canada | 199644.9714 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Main Distribution Switchboard | Main Service Switchboards - 800A to 1600A | Canada | 199644.9714 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Emergency Eyewash Units and Shower Units | Universal/Gender Neutral Washroom Fixtures | Canada | 184302.3138 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. ⚠ Life-safety system — recommend supplemental funding.
2026 | Humanities Fine Arts | Terrazzo Flooring - Cast In Place | Terrazzo Floor | Canada | 166453.8007 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | SIngle door | Interior Doors - Hollow Metal or Wood | Canada | 161607.5711 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Exterior Hollow Metal Door - Double Leaf | Exterior - Revolving Doors | Canada | 160353.7933 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Exterior Hollow Metal Door - Double Leaf | Exterior - Revolving Doors | Canada | 160353.7933 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Fixed Casework - Lab Benches | Millwork General | Canada | 152396.5899 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Gypsum Board Ceiling - Fire Resistant | Painted Ceiling Structures | Canada | 144190.9748 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Exterior Soffits | Exterior Soffits | Canada | 132743.7112 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Exhaust System - Fume Hoods - 1972 | Fume Hood Systems | Canada | 130146.2564 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Painted Floor Finish | Painted / Sealed Floor | Canada | 130118.9949 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Gypsum Board Ceiling - Fire Resistant | Painted Ceiling Structures | Canada | 128903.5919 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Water Heaters | Domestic Water Conditioners - Water Softener Systems | Canada | 117141.1928 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Hollow Metal Single Doors | Interior Doors - Hollow Metal or Wood | Canada | 113894.8596 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Transformer - 75 KVA | Grounding Methods | Canada | 113877.9744 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Transformers - 75 KVA | Grounding Methods | Canada | 113877.9744 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Lighting Fixtures - Exterior | Interior Lighting Systems (Residential) | Canada | 103546.714 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Perimeter Heat - Electric Baseboard | Electric Baseboard Heaters | Canada | 101994.5472 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Perimeter Heat - Electric Baseboard | Electric Baseboard Heaters | Canada | 101994.5472 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Perimeter Heat - Electric Baseboard | Electric Baseboard Heaters | Canada | 101994.5472 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Exhaust System - Fume Hoods - 1997 | Fume Hood Systems | Canada | 97609.6923 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Distribution Equipment - Motor Control Centres | Main Service Panels | Canada | 84599.3165 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Interior Overhead Rolling Doors - 10' x 10' | Interior - Overhead Doors - Industrial | Canada | 82920.8459 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Fume Hood Exhaust Fans | Fume Hood Systems | Canada | 81341.4103 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Lighting Fixtures - Exterior | Interior Lighting Systems (Residential) | Canada | 77660.03 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Interior Hollow Metal Swing Doors - Double Leaf - Rated | Interior Doors - Hollow Metal or Wood | Canada | 74999.4781 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Interior Hollow Metal Swing Doors - Double Leaf - Rated | Interior Doors - Hollow Metal or Wood | Canada | 68477.7844 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Sports and Health Ctr | Interior Hollow Metal Swing Doors - Double Leaf - Rated | Interior Doors - Hollow Metal or Wood | Canada | 65738.673 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Emergency Eyewash Units and Shower Units | Universal/Gender Neutral Washroom Fixtures | Canada | 65078.4988 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. ⚠ Life-safety system — recommend supplemental funding.
2026 | Bespin Auditorium | DX Computer Unit | Refrigerant DX Condensing Units - Under 5 Tons | Canada | 65078.4404 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Distribution Transformer - 300kVA | Grounding Methods | Canada | 65073.1282 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Exhaust System - Fume Hood - Ductwork/Fan (Each) | Fume Hood Systems | Canada | 65073.1282 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Exhaust System - Fans - General Building | Exhaust Fans | Canada | 58578.7107 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Exhaust System - Fume Hood - Ductwork/Fan (Each) | Fume Hood Systems | Canada | 56938.9872 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Fume Hoods | Fume Hood Systems | Canada | 56938.9872 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Exterior Storefront Door - Single Leaf | Exterior - Hangar Doors | Canada | 53540.497 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Emergency Eyewash Units | Universal/Gender Neutral Washroom Fixtures | Canada | 52062.8034 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. ⚠ Life-safety system — recommend supplemental funding.
2026 | Mayo Building | Emergency Eyewash Units and Shower Units | Universal/Gender Neutral Washroom Fixtures | Canada | 52062.8034 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. ⚠ Life-safety system — recommend supplemental funding.
2026 | Mayo Building | DX Condensing Units | Refrigerant DX Condensing Units - Under 5 Tons | Canada | 52062.7524 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Perimeter Heat - Electric Baseboard | Electric Baseboard Heaters | Canada | 50997.2736 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Domestic Water Tank - 435 Litre | Domestic Water Conditioners - Water Softener Systems | Canada | 48808.8303 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Transformer - 75 KVA | Grounding Methods | Canada | 48804.8462 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Transformers - 75 KVA - 1972 | Grounding Methods | Canada | 48804.8462 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Exterior Hollow Metal Door - Single Leaf | Exterior Doors - Hollow Metal | Canada | 48333.6862 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Automatic door openers | Exterior - Automatic Door Openers | Canada | 47163.8165 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Exhaust System - Fume Hood - Ductwork/Fan (Each) | Fume Hood Systems | Canada | 46771.3109 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Exhaust System - Fans - General Building | Exhaust Fans | Canada | 44910.3424 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Emergency Eyewash Units and Shower Units | Universal/Gender Neutral Washroom Fixtures | Canada | 44904.1618 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. ⚠ Life-safety system — recommend supplemental funding.
2026 | Skytop Detector Building | Interior Hollow Metal Swing Doors - Double Leaf | Interior Doors - Hollow Metal or Wood | Canada | 43095.3523 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Motor Control Centres | Main Service Panels | Canada | 42299.6582 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Skytop Detector Building | Interior Hollow Metal Swing Doors - Double Leaf - Rated | Interior Doors - Hollow Metal or Wood | Canada | 40017.1128 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Fan-coil Units | Fan Coil Units | Canada | 39097.9608 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Split DX Unit | Refrigerant DX Condensing Units - Under 5 Tons | Canada | 39047.0643 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Water Heater - Elec - Residential - 85 Gallon | Domestic Water Conditioners - Water Softener Systems | Canada | 39047.0643 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Interior Doors - Special | Other Interior Doors | Canada | 37499.7427 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Transformer - 45 KVA | Grounding Methods | Canada | 37417.0458 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Transformers - 45 KVA - 1972 | Grounding Methods | Canada | 37417.0458 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Roof top stairs | Exterior (Attached) Stair Construction | Canada | 36327.2899 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Exterior Hollow Metal Door - Single Leaf | Exterior Doors - Hollow Metal | Canada | 35304.6081 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Exhaust System - Fans - General Building | Exhaust Fans | Canada | 33682.755 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Exhaust System - Fans - General Building | Exhaust Fans | Canada | 33682.755 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Water Heater - Elec - 85 Gal | Domestic Water Conditioners - Water Softener Systems | Canada | 33678.0922 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Water Heater - Gas - 76 Gallon | Domestic Water Conditioners - Water Softener Systems | Canada | 33678.0922 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Interior Automatic Openers - Single | Automatic Door Openers | Canada | 32296.9598 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Condensing Unit | Refrigerant DX Condensing Units - Under 5 Tons | Canada | 29936.0811 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Interior Automatic Openers - Single | Automatic Door Openers | Canada | 25632.5076 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Communal Washrooms | Communal Washroom Refurbishment | Canada | 25297.889 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Steel framed guardrails | Exterior Guards and Railings | Canada | 25167.5427 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Exterior Storefront Door - Double Leaf | Exterior Doors - Aluminum and Glass | Canada | 24105.2674 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Exterior Storefront Door - Double Leaf | Exterior Doors - Aluminum and Glass | Canada | 24105.2674 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Lando Gym | Exterior Storefront Door - Single Leaf | Exterior Doors - Aluminum and Glass | Canada | 24105.2674 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Water Heater - Elec - Residential - 40 Gallon | Domestic Water Conditioners - Water Softener Systems | Canada | 22452.059 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Water Tank Heater - 2005 | Domestic Water Conditioners - Water Softener Systems | Canada | 22452.059 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | The Mustafar Visitor Center | Water Tank Heater - 2011 | Domestic Water Conditioners - Water Softener Systems | Canada | 22452.059 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Distribution Equipment - Motor Control Centre | Main Service Panels | Canada | 22207.3177 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Distribution Equipment - Motor Control Centres | Main Service Panels | Canada | 22207.3177 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Exterior Hollow Metal Door - Single Leaf | Exterior Doors - Hollow Metal | Canada | 21014.6449 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Water Coolers - Wall Mounted (Each) | Bidets | Canada | 20508.1747 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Exhaust System - Fans - General Building | Exhaust Fans | Canada | 20502.5487 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Split Condensing Unit | Refrigerant DX Condensing Units - Under 5 Tons | Canada | 20499.7102 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Water Heater - Elec - Residential - 143 Litre | Domestic Water Conditioners - Water Softener Systems | Canada | 20499.7102 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Exhaust System - Fume Hood | Fume Hood Systems | Canada | 20335.3526 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Exhaust System - Fume Hood - Ductwork/Fan | Fume Hood Systems | Canada | 20335.3526 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Walk-in Coolers and Freezers | Basketball Backboards - Fixed | Canada | 20238.3244 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Unit Heaters | Unit Heaters (Hydronic) | Canada | 19123.9776 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Water Fountains | Drinking Water Fountains (Non-refrigerated) | Canada | 19123.9776 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Sump Pump - Submersible - 1/2 HP | Sanitary Waste Ejector Pumps | Canada | 17849.0677 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Transformers - 30 KVA & 15 KVA | Grounding Methods | Canada | 17081.6932 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Exterior Storefront Door - Single Leaf | Exterior - Hangar Doors | Canada | 16731.4081 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | DX Ductless Split Unit | Refrigerant DX Condensing Units - Under 5 Tons | Canada | 16269.6101 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | DX Ductless Split Unit | Refrigerant DX Condensing Units - Under 5 Tons | Canada | 16269.6101 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Split DX Ductless Unit - 2 Tons | Refrigerant DX Condensing Units - Under 5 Tons | Canada | 16269.6101 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Walk-in Coolers and Freezers | Basketball Backboards - Fixed | Canada | 16062.1637 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Fixed Casework - Lab Benches | Bleachers | Canada | 14991.2414 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Exterior Automatic Openers - Single | Exterior - Automatic Door Openers | Canada | 12816.2538 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Custodial Sinks | Custodial Sinks | Canada | 12749.3184 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Unit Heaters - Hot Water | Unit Heaters (Hydronic) | Canada | 12749.3184 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Water Coolers | Bidets | Canada | 12207.2462 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Exhaust System Fans | Exhaust Fans | Canada | 12203.8968 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Split DX Ductless Unit - 1.5 Tons | Refrigerant DX Condensing Units - Under 5 Tons | Canada | 12202.2112 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Science | Water Heater - Elec - 20 Gallon | Domestic Water Conditioners - Water Softener Systems | Canada | 12202.2112 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Exterior Storefront Door - Double Leaf | Exterior Doors - Aluminum and Glass | Canada | 11004.5765 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Sump Pump - Submersible - 1/2 HP | Sanitary Waste Ejector Pumps | Canada | 10624.4466 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Mayo Building | Interior Hollow Metal Swing Doors - Double Leaf - Rated | Interior Doors - Hollow Metal or Wood | Canada | 10434.71 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Humidity Control Equipment - Steam Humidification | Fuel-Fired Humidifiers | Canada | 10167.6763 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Humidity Control Equipment - Steam Humidification | Fuel-Fired Humidifiers | Canada | 10167.6763 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Humidity Control Equipment - Steam Humidification | Fuel-Fired Humidifiers | Canada | 10167.6763 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Bespin Auditorium | Water Heater - Elec - 43 Litre | Domestic Water Conditioners - Water Softener Systems | Canada | 9761.7661 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Humidity Control Equipment - Steam Humidification | Fuel-Fired Humidifiers | United States | 9504.81 | P3–Imminent Breakdown | 2 - Good | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Water Coolers | Bidets | Canada | 9155.4364 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Water Coolers | Bidets | Canada | 9155.4364 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Water Coolers | Bidets | Canada | 9155.4364 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Custodial Sinks | Custodial Sinks | Canada | 8499.5456 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Custodial Sinks - 1972 | Custodial Sinks | Canada | 8499.5456 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Custodial/Utility Sinks | Custodial Sinks | Canada | 8499.5456 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Drinking Water Fountains | Drinking Water Fountains (Non-refrigerated) | Canada | 6374.6592 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Unit Heaters - Electric (Each) | Unit Heaters (Hydronic) | Canada | 6374.6592 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Kamino Student Ctr | Single doors | Interior Doors - Hollow Metal or Wood | Canada | 5478.2227 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Custodial Sinks - 2000 | Custodial Sinks | Canada | 4249.7728 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Hand-wash Sinks | Sinks | Canada | 4249.7728 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2026 | Humanities Fine Arts | Handwash & Kitchen Sinks | Sinks | Canada | 4249.7728 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2027 | The Mustafar Visitor Center | Acoustic Tile Ceiling - Exposed T-bar | Suspended Acoustic Panel Ceiling | Canada | 7015434.948 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2027 | The Mustafar Visitor Center | Acid Resistant Sheet Vinyl | Masonry and Stone Floor | Canada | 6563809.5756 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2027 | The Mustafar Visitor Center | DDC System | Direct Digital Control Systems | Canada | 4617994.6963 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2027 | Science | Fire Alarm System - Wiring | Fire Alarm Systems | Canada | 2745287.1864 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. ⚠ Life-safety system — recommend supplemental funding.
2027 | Science | Emergency Battery Pack | Emergency Lighting Systems | Canada | 2703364.0342 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. ⚠ Life-safety system — recommend supplemental funding.
2027 | Skytop Detector Building | Clock System | Clock and Program Systems | Canada | 1676510.9476 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2027 | Skytop Detector Building | Sealed Concrete Floor | Painted / Sealed Floor | Canada | 1659051.7969 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2027 | Bespin Auditorium | Painted Ceiling | Painted Ceiling Structures | Canada | 1024108.7648 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2027 | Mayo Building | Urethane Flooring | Painted / Sealed Floor | Canada | 680230.6739 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2027 | Lando Gym | Epoxy Painted Ceiling | Painted Ceiling Structures | Canada | 320362.229 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2027 | Skytop Detector Building | Automatic Door Operators | Automatic Door Openers | Canada | 249230.0183 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2027 | Lando Gym | Water Heater - 2015 - 322 L | Domestic Water Conditioners - Water Softener Systems | Canada | 34688.435 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2027 | Lando Gym | Water Heater - 85 Gallon - 2011 | Domestic Water Conditioners - Water Softener Systems | Canada | 34688.435 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2027 | Lando Gym | Water Heater - Domestic Hot Water | Domestic Water Conditioners - Water Softener Systems | Canada | 34688.435 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2027 | Lando Gym | Water Heater - Fish Lab | Domestic Water Conditioners - Water Softener Systems | Canada | 34688.435 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
2027 | Lando Gym | Loading Dock Equipment | Loading Dock Truck Levellers | Canada | 18867.0686 | P4–Proactive Replacement | 4 - Poor | Excluded – budget constraint. Poor condition — proactive replacement needed to avoid unplanned failure.
TOTAL DEFERRED HIGH-RISK EXPOSURE (276 items) |  |  |  |  | 307616831.9865